## Sheet1
Project: Connect 4
Team Members: Abhishek Bais, Haley Feng, Princy Joy, Shannon Phu
Team Lead:
Summary: |  | Connect Four is a two player game in which players select different colored circular
pieces, take turns to drop them in a 6x7 grid. The first player to place four of their
pieces consecutively in a row, column, or a diagonal line wins. A computer’s agent can
learn to play Connect Four using reinforcement learning techniques, compete against
human opponents and place pieces to win the game.
Timeline: |  | 10/24/2021 -to-12/05/2021
SPRINT [1] BACKLOG
ID | User Story | Tasks | Owner | Status | Estimated effort (man weeks) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 5
CF001 |  | Perform background research on playing Connect 4 using RL agent | All | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0
CF002 |  | Implement MinMax approach | Abhishek Bais | In Progress | 2 | 0 | 1 | 1 | 0 | 0 | 0
CF003 |  | Implement Q approach | Haley Feng | In Progress | 2 | 0 | 1 | 1 | 0 | 0 | 0
CF004 |  | Implement Policy gradient descent approach | Princy Joy | In Progress | 2 | 0 | 1 | 1 | 0 | 0 | 0
CF005 |  | Implement Tabular Q learning approach | Shannon Phu | In Progress | 2 | 0 | 1 | 1 | 0 | 0 | 0
CF006 |  | Evaluate different approaches | All | Planned | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0
CF007 |  | Improve models for different approaches | All | Planned | 1.5 | 0 | 0 | 0 | 0.5 | 1 | 0
CF008 |  | Perform comparitive study | All | Planned | 1 | 0 | 0 | 0 | 0 | 1 | 0
CF009 |  | Prepare Report | All | Planned | 1 | 0 | 0 | 0 | 0 | 0 | 1